| Project Management | University of Debrecen Faculty of Economics and Business Administration Department of Management and Marketing | A |
| --- | --- | --- |
| Mid-term paper; Date: …….. / ..……. / ..……. |  |  |

Name: ……………………………………………………..   	BA in BMA / Erasmus / SSE specialsation

Do not forget to fill the Answer Sheet on the first page! Time limit: 40 minutes.

Answer Sheet

Total Points: 30 (15 multiple choice + 15 calculation&plotting)

Exercise 1. Multiple Choice (maximum points: 15)	Points: …….. / 15

| 1 | C | 5 | B | 9 | C | 13 | A |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | A | 6 | C | 10 | D | 14 | B |
| 3 | A | 7 | B | 11 | A | 15 | B |
| 4 | D | 8 | C | 12 | B |

Exercise 2 (maximum points: 10)

Total Project Time (TPT) = ……………… days

Exercise 3 (maximum points: 5)

Current schedule performance index (SPI) 	= ………………

Total current estimated time slip 	= ………………

Planned time to complete 	= ………………

Current estimated time to complete (ETC) 	= ………………

Current estimated Total Project Time (TPT)  	= ………………

Exercise 1: Multiple Choice (only one answer is correct)

|  | A …….. schedule variance with …….. cost variance suggests a project running late with an overspend. negative; zero negative; positive negative; negative zero; positive |
| --- | --- |
|  | The elements of the project triangle are: Quality of the project product, time and costs. Cost, resources and time. Project product specifications, control and planning. Planning controlling and quality. |
|  | Reducing activity durations by …. is the process when successor activities are started before their predecessors ended. overlapping activities increased risk paralelled activities the transference of resources |
|  | Appointment of the project manager and the project management team takes place in the … phase of the project life cycle. Termination Definition Implementation Development |
|  | Planning a project, the first document that should be developed from the list below is the … WBS (work breakdown structure) SOW (statement of work) network diagram responsibility matrix |
|  | … is connected to the level of sophistication in the organisation’s best practices for managing projects. Parochialism Dissemination Project management maturity Project-matrix |
|  | Which one of the following is a disadvantage of the project-matrix structure: Slow response to changes It is hard to ensure the common view and acceptation of the organisational goals and objectives Definition of responsibility and authority is not clear Over-specialisation |
|  | The utilisation in repetitive activities is the best in organisations with …. true project structure matrix structure hierarchical functional structure divisional structure |
|  | To permit effective tactical decision making strategy should be: implicit complicated capable of being monitored focused on operations |
|  | The effective … contains introduction and background, technical description, timeline and milestones, client expectations. Gozinto chart work breakdown structure project network technique statement of work |
|  | Project milestones are sometimes called … project deliverables deadlines work packages project phases |
|  | In the Logical Framework Matrix the … is of great importance in clarifying the extent to which project objectives depend on external factors. Indicators column Risks and assumptions column Strategic goal cell Indicators row |
|  | … is a systematic examination of the methods of carrying out activities to increase the effectiveness and efficiency of the whole work system. The questioning method is a frequently used technique from this approach. work study PNTs controlling Balanced Scorecard |
|  | The ability of an item to perform a required function under given conditions for a given time interval. Durability. Reliability Validity. Quality. |
|  | Re-drawing the network diagram leaving out all those activities that are complete and re-analyse the others is a possible way of the … technique(s). negative float re-analysing cost-control disintermediaton |

Calculation & plotting exercises (in the mid-term there will be 2 exercises) (max. points: 15)

Exercise 2

Given the following data, plot a Gantt chart for the full project with the minimum possible Total Project Time, and calculate the TPT. The final version of the Gantt should be plotted on the answer sheet.

Number of identical project workers: 2 (names are X and Z)

Activities with durations: A (1 day), B (2 days), C (4 days), D (3 days), E (2 day), F (4 days), G (1 day)

Activities that can be done by 2 workers (duration reduced to half): B, C, E, F

Possible overlapping: C, F (1 day before the predecessor activity ends)

Possible paralleling (no precedence relationship): D and E

Exercise 3

There is a project with a planned Total Project Time (TPT) of 13 days. There are 4 non-overlapping work packages with durations 1, 2, 4 and 6 days. After 4 days the first work package is totally completed, and 50% of the second and 25% of the third work package is also done. The last one is not started yet. Calculate the

- current schedule performance index (SPI)

- total current estimated time slip

- planned time to complete

- current estimated time to complete (ETC)

- current estimated Total Project Time (TPT)