## Slide 1: Controlling cost
(lecture + seminar)

## Slide 2: Why control cost?
To satisfy financial auditors and support data for the government (obligatory).
To satisfy the information needs of the project team.
Why the first one is not enough?
In projects speed is more important than accuracy (within 5% it is acceptable).

## Slide 3: Importance of cost control
Importance is greater than of other resources:
  reduction of profit or
  bankruptcy unless costs are paid by the customer;
  in the latter case: closer control from the customer or/and abrogation of the contract
Aims by the type of contract:
  cost-plus: controlling
  fixed-price: reducing

## Slide 4: Control during the project cycle
Types of cost occurrences
Availability of money
Measuring level:
Hammocks (e.g. for overhead costs)
per activity
6 features of control systems:
Plan
Publish
Measure
Compare
Report
Forecast and correct

## Slide 5: Cost control
Traditional: (actual cost incurred)t / (planned expenditure)t
Critique?
not reveal possible problems (e.g. late activities with increased cost)
Sometimes natural resource quantities are more effective measures (or only these are available). These should be measured separately.

## Slide 6: Earned value analysis
Replaces the traditional cost control practices.
Based on assigning value in cost, manhours or any other appropriate measure at the task level to the achievement of work.
Measures the project achievement for the incurred costs.
Aims are problem identification and correction.

## Slide 7: How to illustrate Earned Value?
planned cost
now
estimated budget
earned value
actual cost
Cost schedule variance

## Slide 8: Budget preparation
Data collection
WBS
Cost centre codes (OBS)
Indirect expenses & the use of hammocks
  direct
  overhead (indirect)
c
d
e
f
hammock
Overhead cost for the c-d-e-f activities presented by a hammock „activity”:

## Slide 9: Data collection
Novelty:
Estimates of work new for the organisation
Prepared from more detailed breakdown of the project than in a normal budgeting process
It is useful to consider the effect of the information source on the data
Cost data = f(resource data, time data)

## Slide 10: WBS
Work packages:
  clearly defined and manageable
  contains elemental tasks
Definition of a WP:
  all relevant information on labour, equipment, material, overhead etc. rates

## Slide 11: Cost centre codes
OBS
Cost Breakdown Structure
  1 responsible person on every level
Organisation of these codes are project specific and different from the organisation’s existing system

## Slide 12: Finalisation of the budget preparation
GANTT/PNT with cost associated to each activity
Code defining the cost centre to which each activity is assigned
Name of each single person responsible for the control of each activity cost

## Slide 13: The budgeting system
Three sets of figures:
  Planned costs
  Committed costs
  Actual costs

## Slide 14: Planned and actual costs
Planned cost – Committed cost = Cost variance
Variance can be positive or negative
Negative variance is always bad, but the positive is not necessarily good.

## Slide 15: Examples
What is the variance if the budgeted cost is 200 and the actual cost is 250?
What is the actual cost if the budgeted cost is 2000 and the variance is 500?
What is the planned cost, if the actual cost is 120 and the variance is -30?
Planned cost – 120 = -30 thus
Planned cost = 90
2000 – actual cost = 500 thus
Actual cost = 1500
200 – 150 = variance thus
Variance = -50

## Slide 16: 3+1 alternative sources of a positive variance
Good control
Some outgoing not recorded
Some activity costs overestimated
+
Activities for the period in question are not finished



costs:planning:

## Slide 17: 3 alternative sources of a negative variance
Poor control
Extra unbudgeted work was included
Some activity costs were underestimated




## Slide 18: Example
There is a project with three activites planned for a year
  ‘a’ with a planned cost of 1000,
  ‘b’ with a planned cost of 500 and
  ‘c’ with a planned cost of 1500.
‘a’ activity turned out to be more expensive (with an additional 200).
‘b’ was done as budgeted.
‘c’ is not finished in the year, and only 1000 was spent on it.
An additional ‘d’ activity was needed and performed with a cost of 300.
What is the cost variance for the given year?
What is the conclusion on the cost performance?
(1000+500+1500) – (1200+500+1000+300) = 0

## Slide 19: How to find out the true reason?
Improving the data : percentage of activity remaining percentage of activity completed
Variance analysis:
  Variance can be broken down into a set of subbudget variances (like labour, overhead etc.)
  A subbudget variance may be split into:
    Volume/quantity variance
    Rates/prices variance

## Slide 20: Cost & schedule variances
For any instant we can calculate:
  BCWS: budgeted cost of work scheduled
  BCWP: budgeted cost of work performed
  ACWP: actual cost of work performed
From these, two variances can be derived:
  Schedule variance in cost terms = BCWP – BCWS
  Cost variance = BCWP – ACWP

## Slide 21: Cost & schedule variances
 | negative | zero
negative | Running late with overspent | Running late but no overspent
zero | On time but overspent | On time and no overspent
Cost variance
Schedule variance

## Slide 22
Notes: OD = original duration planned for work performed; ATE = actual time expended to date

## Slide 23: Example
Project data:
Representative survey project with 300 given addresses and 3 interviewers
Interviewers are paid as follows:
  1000 HUF per day per interviewer as a fixed pay
  400 HUF per interview as a variable pay
Time schedule:
  10 interviews per day per interviewer
  Work packages: 30 interviews per day
Calculate the BCWS for every work package & day.
Given the following progress report for the first 6 days, calculate the percentages of activity completed, the BCWP and the ACWP.

## Slide 24
 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
A |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  |  |  | 
H |  |  |  |  |  |  |  |  |  | 
I |  |  |  |  |  |  |  |  |  | 
J |  |  |  |  |  |  |  |  |  | 
BCWS |  |  |  |  |  |  |  |  |  | 
BCWP |  |  |  |  |  |  |  |  |  | 
ACWP |  |  |  |  |  |  |  |  |  | 
15000 30000 45000 60000 75000 90000 105000 120000 135000 150000
15000
15000
15000
15000
15000
15000
15000
15000
15000
15000

## Slide 25: Progress report
 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
A | 18 | 8 | 4 |  |  |  |  |  |  | 
B |  | 16 | 10 | 4 |  |  |  |  |  | 
C |  |  | 14 | 10 | 0 | 0 |  |  |  | 
D |  |  |  | 12 | 6 | 6 |  |  |  | 
E |  |  |  |  | 16 | 8 |  |  |  | 
F |  |  |  |  |  | 12 |  |  |  | 
G |  |  |  |  |  |  |  |  |  | 
H |  |  |  |  |  |  |  |  |  | 
I |  |  |  |  |  |  |  |  |  | 
J |  |  |  |  |  |  |  |  |  | 
BCWS | 15000 | 30000 | 45000 | 60000 | 75000 | 90000 | 105000 | 120000 | 135000 | 150000
BCWP |  |  |  |  |  |  |  |  |  | 
ACWP |  |  |  |  |  |  |  |  |  | 

## Slide 26: Progress report
 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
A | 18 60% | 8 87% | 4 100% |  |  | 
B |  | 16 53% | 10 87% | 4 100% |  | 
C |  |  | 14 47% | 10 80% | 0 80% | 0 80%
D |  |  |  | 12 40% | 6 60% | 6 80%
E |  |  |  |  | 16 53% | 8 80%
F |  |  |  |  |  | 12 40%
G |  |  |  |  |  | 
H |  |  |  |  |  | 
I |  |  |  |  |  | 
J |  |  |  |  |  | 
BCWS | 15000 | 30000 | 45000 | 60000 | 75000 | 90000
BCWP | 9000 | 21000 | 35100 | 48000 | 59000 | 72000
ACWP | 10200 | 22800 | 37000 | 50400 | 62800 | 75600

## Slide 27: Calculate the variances for day 6
Schedule variance in cost terms = BCWP – BCWS
72000 – 90000 = -18000
Cost variance = BCWP – ACWP
72000 – 75600 = -3600
The project is running late and overspent.

## Slide 28: Forecasting and comparison of projects
Schedule performance index (SPI) = BCWP/BCWS
Cost performance index (CPI) = BCWP/ACWP
Budgeted cost to complete (BCC) = BAC - BCWP
Estimated cost to complete (ECC) = BCC/CPI
Forecast cost at completition (FCC) = ACWP+ECC
Calculate these for the previous example.
Notes: BAC = budget at completition =budgeted cost of the whole project

## Slide 29: Solution
BAC = 150 000
CPI = 72 000 / 75 600 = 95.24%
SPI = 72 000 / 90 000 = 80.00%
BCC = 150 000 – 72 000 = 78 000
ECC = 78 000 / (720/756) = 81 900
FCC = 75 600 + 81 900 = 157 500

## Slide 30: Problem solving
a
b
d
e
c
There is a small project with the following network diagram:
The following table contains the information on the activity durations and costs:
Activity label | Duration (day) | Cost of the activity
a | 1 | 100
b | 1 | 50
c | 2 | 60
d | 3 | 90
e | 2 | 40
Plot a Gantt chart from the information above and calculate the BCWS for every day of the project.

## Slide 31: Solution
task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
A | 100 |  |  |  |  |  | 
B |  | 50 |  |  |  |  | 
C |  | 30 | 30 |  |  |  | 
D |  |  | 30 | 30 | 30 |  | 
E |  |  |  |  |  | 20 | 20
BCWS | 100 | 180 | 240 | 270 | 300 | 320 | 340

## Slide 32: Problem solving
In the previous project, the project manager receives a progress report of the first 4 days, with the following information:
  Activity ‘a’ is completed
  Activity ‘b’ is completed
  Activity ‘c’ is 50% completed
  Activity ‘d’ is 33.33% completed
  Costs are calculated with completition ratio
Calculate BCWP and ACWP for the first 4 days
Calculate CPI, SPI, BCC, ECC and FCC

## Slide 33: Solution
BCWP = ACWP = 100 + 50 + 0.5(60) + 0.33(90) = = 210
CPI = BCWP / ACWP = 1
SPI = BCWP / BCWS = 210 / 270 = 0.78
BCC = BAC – BCWP = 340 – 210 = 130
ECC = BCC / CPI = 130
FCC = ACWP + ECC = BAC / CPI = 340

## Slide 34: Reading
Textbook chapter 10

## Slide 35: Thank you for listening