## Slide 1: Line of Balance (LoB) and elemental trend analysis
Project management

## Slide 2: Line of Balance (LoB)
A conventional network technique applied to develop and control a single batch.
It was developed as a production planning tool before the time of PNTs.
It has a much less wide application area.

## Slide 3: Requirements of LoB
Identifiable stages in production to exert managerial control.
Known manufacturing times between stages.
Delivery schedule.
Resources can be varied as required.

## Slide 4: Elemental trend analysis (= LoB) requirements
Items in the batch are independent of each other
Same resource carries out the same activity on every item in the batch
Only one resource can work on a given item at a time
Any resource constraints must be removed before the analysis

## Slide 5: Where it is useful?
Construction industry
Heavy engineering assembly
Road or railway building
…
Why not using a PNT here?

## Slide 6: Problem solving example
There is a project of building 5 identical row-houses.
On each house 4 work units (items) should be completed, each one is performed by a specialized team of workers:
  Foundations (Team A): 1 month per house,
  Brickwork (Team B): 2 months per house,
  Roof construction (Team C): 2 weeks per house,
  Internal works (Team D): 1 month per house
Plot a LoB chart. Follower team can start working on a given unit immediately after the predecessor team finished. Calculate the TPT.
Redesign the LoB chart to eliminate idle times with the least possible increase in the TPT.

## Slide 7: Solution (a)
Month 1
Month 4
Month 3
Month 2
Month 6
Month 5
Month 7
House 1
House 3
House 2
House 4
House 5
Month 8
Month 11
Month 12
Month 9
Month 10
TPT 12 .5 months
Month 13

## Slide 8: Solution (b)
Month 1
Month 4
Month 3
Month 2
Month 6
Month 5
Month 7
House 1
House 3
House 2
House 4
House 5
Month 8
Month 11
Month 12
Month 9
Month 10
TPT 14.5
months
Month 13
Month 14

## Slide 9: Control with LoB
If the 2nd team performing only on 75%...

## Slide 10: Control with LoB
Month 1
Month 4
Month 3
Month 2
Month 6
Month 5
Month 7
House 1
House 3
House 2
House 4
House 5
Month 8
Month 11
Month 12
Month 9
Month 10
Month 13
Month 14
Month 15
Month 16
Month 17
TPT 17
months

## Slide 11
Problem solving example No2
There is a project of planting 4 identical trees in a botanical garden.
Planting a tree requires 4 steps of work (each done by a different person):
  digging: 15 mins
  prepare the hole for the tree with special nutrients: 5 mins
  placing the tree into the hole: 10 mins
  tidy up the surroundings of the tree: 5 mins
Plot a LoB chart. Follower worker can start working on a given unit of work immediately after the predecessor team finished. Calculate the TPT.
Redesign the LoB chart to eliminate idle time of teams increasing the TPT with only the possible minimum.

## Slide 12: Thanks for the attention