| Project Management | University of Debrecen Faculty of Economics and Business | A |
| --- | --- | --- |
| Mid-term paper; Date: …….. / ..……. / ..……. |  |  |

Name: ……………………………………………………..   	BA in BMA / Erasmus / SSE specialsation

Do not forget to fill the Answer Sheet on the first page! Time limit: 45 minutes.

Answer Sheet

Total Test Score: 50 (15 multiple choice + 35 calculation&plotting)

The percentage points for the final grade is 0.3(Total Test Percentage)

Exercise 1. Multiple Choice (maximum points: 15)	Points: …….. / 15

| 1 |  | 5 |  | 9 |  | 13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 |  | 6 |  | 10 |  | 14 |  |
| 3 |  | 7 |  | 11 |  | 15 |  |
| 4 |  | 8 |  | 12 |  |

Exercise 2 (maximum points: 15)

PTPT = …………….. (1 pt);  	ATWP = …………….. (1 pt);  	PTWP = …………….. (2 pt);

PTC = …………….. (2 pt);   	 SPI = …………….. (3 pt);    	ETC = …………….. (2 pt);

ETPT = …………….. (2 pt);    	 estimated time slip = …………….. (2 pt);

Exercise 3 (maximum points: 20)

PTPT = …………….. (1 pt);  	ACWP = …………….. (1 pt);  	BAC = …………….. (1 pt);

BCWS = …………….. (2 pt);  	BCWP = …………….. (2 pt);

SPI = …………….. (2 pt);    	CPI = …………….. (2 pt);

BCC = …………….. (2 pt);   	ECC = …………….. (2 pt);   	FCC = …………….. (2 pt);

ETPT = …………….. (2 pt);     	estimated time slip = …………….. (1 pt);

Exercise 1: Multiple Choice (only one answer is correct)

|  | A …….. schedule variance with …….. cost variance suggests a project running late with an overspend. negative; zero negative; positive negative; negative zero; positive |
| --- | --- |
|  | The elements of the project triangle are: Quality of the project product, time and costs. Cost, resources and time. Project product specifications, control and planning. Planning controlling and quality. |
|  | Reducing activity durations by …. is the process when successor activities are started before their predecessors ended. overlapping activities increased risk paralleled activities the transference of resources |
|  | Appointment of the project manager and the project management team takes place in the … phase of the project life cycle. Termination Definition Implementation Development |
|  | Planning a project, the first document that should be developed from the list below is the … WBS (work breakdown structure) SOW (statement of work) network diagram responsibility matrix |
|  | There are 3 competing project proposals. Their expected profits are: A = 100, B = 150, C = 200. What is the opportunity cost of choosing proposal ‘C’? 100 b) 150 c) 200 d) 250 |
|  | Which one of the following is a disadvantage of the project-matrix structure: Slow response to changes It is hard to ensure the common understanding of the importance of projects Definition of responsibility and authority is not clear Over-specialisation |
|  | The utilisation in repetitive activities is the best in organisations with …. true project structure matrix structure hierarchical functional structure divisional structure |
|  | To permit effective tactical decision making strategy should be: implicit complicated capable of being monitored focused on operations |
|  | The effective … contains introduction and background, technical description, timeline and milestones, as well as client expectations. Gozinto chart work breakdown structure project network technique statement of work |
|  | Project milestones are sometimes called … project deliverables deadlines work packages project phases |
|  | The ‘d’ activity in the picture on the right is… a hammock activity a dangling activity a looping activity a dummy activity |  |
|  | … is a systematic examination of the methods of carrying out activities to increase the effectiveness and efficiency of the whole work system. The questioning method is a frequently used technique from this approach. work study PNTs controlling Balanced Scorecard |
|  | The ability of an item to perform a required function under given conditions for a given time interval. Durability. Reliability Validity. Quality. |
|  | Which one is least possible to be managed like a project? Baking the daily quantity of bread in a bakery. Organizing a wedding for a wedding organizer company, with fix-priced contract Trying to win the lottery. Writing a book by a professional writer, according to a detailed (topic, deadline, cost, pages) contract. |

Calculation & plotting exercises (in the mid-term there will be 2 exercises) (max. points: 35)

Exercise 2 (15 pts)

There is a project with 4 non-overlapping work packages with durations 1, 2, 4 and 6 days. After 4 days the first work package is totally completed, and 50% of the second and 25% of the third work package is also done. The last one is not started yet. Based on the first 4 days’ data calculate the PTPT, the ATWP, the SPI, the PTWP, the PTC, the ETC, the ETPT, and the expected time slip.

Exercise 3 (20 pts)

There is a project with the following planned data:

| Activity label Duration (day) Daily cost of the activity a 2 10 b 1 20 c 4 20 d 3 30 e 2 10 |  |
| --- | --- |

After 5 days, the monitoring system provides the following information:

  - Activity ‘a’ is completed

  - Activity ‘b’ is completed

  - Activity ‘c’ is 50% completed

  - Activity ‘d’ and ’e’ are 0% completed (not even started)

  - Money spent: 100

- Calculate BCWS, BCWP and ACWP for the first 5 days

- Calculate PTPT; BAC, CPI, SPI, BCC, ECC, FCC, ETPT, and the estimated time slip.

# Text boxes

a

b

d

e

c